## Sheet1
ID | Risk Description | Likelihood | Impact | Severity | Owner | Mitigation | Status
1 | Underestimated the time required to complete the project requirements | Low | Low | Medium | Self | Discuss the project requirements with the superviser and create a clear project plan | Open
2 | Inadequate knowledge on Python and Machine Learning | Low | Medium | Medium | Self | Go through tutorials as required and seek help from supervisor as required | Open
3 | Interruption in project progress due to COVID-19 or other health issues | Low | High | Medium | Self | Take preventive measure and take good care of health. Consult to a doctor if required and inform the supervisor in case of difficulty | Open
4 | Hardware/ Internet Failure | Low | Low | Low | Self | Repair hardware as required. Contact ISP for quick fix of the internet. Use mobile data/ hotspot as an alternative. | Open
5 | Lack of adequate dataset/ labelled audio data for the model training | Low | High | Medium | Self | Research required audio data through internet. If needed, consult with SSD to take help from fellow students for data collection. | Open
6 | Lack of hardware infrastructure for model training | Medium | Medium | Medium | Self | Try lowering the processing requirements through training arguments or use cloud computing technology like Google Colab if required | Open